## Slide 1: Prescribing Proportionate Care
Sophie Coles
(Lead Practitioner, Transformation Team
(Occupational Therapist))
Cameron Raeburn
(Manual Handling Lead, NHS Forth Valley
(Physiotherapist))

## Slide 2: Agenda
Introduction
“The Why”
Procurement
Equipment Audit
Reflections

## Slide 3: Setting the Scene
Whole systems approach
Hospitals were in crisis
Unmet demand in community resulting in unnecessary admissions

## Slide 4
How important
is it really?
https://www.communitycare.co.uk/2021/08/27/local-authorities-delivering-social-care-facing-2-1bn-black-hole/
14 April 2022
Progress on waiting times - but social care must be supported to free up hospital beds, says NHS leader (homecareinsight.co.uk)
20 April 2022
Jeremy Hunt, chair of the Health and Social Care Committee has previously said that funding from the Health and Social Care Levy (1.25% tax on earnings) will fail to tackle hospital waiting lists without proper investment in home care.
The former Health Secretary said “it is very short-sighted” of the government not to have invested adequate funding into home care, and the social care sector in general, because it means important targets will be missed.
40,000 put at risk last month’ while waiting in ambulance | News | Health Service Journal (hsj.co.uk)​
​
29 April 2022

## Slide 5: Key Drivers
Reducing Delayed Discharges | Over the period July 2020 – July 2021, delayed discharges cost Forth Valley £6.4m (25,106 days). The latest figures show that in December 2021; 69% of delays (102 people) were due to health & social care reasons.
Reducing Unnecessary Admissions | A significant risk is posed to the Health & Social Care Partnerships if critical Care at Home cannot be delivered. Further demands will then be placed on acute services.
Improving Proportionate Assessment Skills | Ensuring effective and efficient use of resources is essential. In excess of 15% Care at Home demand has been added to the system since the start of the pandemic. 15 new double-handed packages per month over 2020-2021 were requested within the Stirling area, as an example.
Improving Integration of Workforce through Training | On an organisational level, streamlining professional working practices and gaining shared knowledge through joint training is a way in which the Partnerships will quickly improve effectiveness.

## Slide 6: Community Statistics (8th December 2021)
Stirling
212 people were awaiting a package of care being provided.
A total of 2,664 hours per week.
Clackmannanshire
93 people were awaiting a package of care being provided.
A total of 643 hours per week.
Falkirk
339 people were awaiting a package of care being provided.
A total of 2,631 hours per week.

## Slide 7: “Leadership is the capacity to translate vision into reality”.

## Slide 8: SBAR compiled for Gold Command

## Slide 9: A significant risk is posed to HSCPs if critical Care at Home cannot be delivered. Further demands will then be placed on acute services.
% Reduction in total Packages of Care provided | Hours released (per week)
5 | 544
10 | 1,088
15 | 1,632
20 | 2,176
25 | 2,720
30 | 3,263
35 | 3,807
40 | 4,351
There were 485 people receiving existing double-up care packages across the Forth Valley area in Oct 2021 (10,878 hours).
The calculations below demonstrated the potential number of hours which could be redistributed to reduce unmet needs.
Calculation of potential release of hours:-

## Slide 10: Key Benefits
Release of Care Hours | Across the UK, 62 Councils / NHS Trusts have reviewed double-handed packages utilising the skills gained through the Prescribing Proportionate Care approach training delivered by A1 Risk Solutions. Between 40%- 89% reduction in double-handed packages has been achieved across these areas. A1 Risk Solutions are supporting NHS England / NHS Improvement to introduce Single Handed Care into NHS acute services. A 40% reduction would enable release of 4.4k hours per week back into the system. 4.4k hours at an average cost per hour of £20 totals £87,000 per week; a total return of £4.5m per annum.
Achieving Strategic & National Outcomes | By releasing capacity and enabling essential care staff to pick up unresourced care packages; the Partnerships ensure that they support people to remain at home safer and for longer. Independent Living / Positive Experiences & Outcomes / Quality of Life / Carers are Supported / People are Safe / Engaged Workforce / Resources are used Efficiently & Effectively
Financial Impact | Through reducing delayed discharges, there is an improvement to patient flow through the system; but also, a financial benefit to the budget, remembering the £6.2m cost of delayed discharges last year.
Sustainability | Through delivering a whole systems training approach; the Partnerships maximise the sustainability around increasing care hour capacity in a safe manner, ensuring portability of the workforce across Forth Valley.

## Slide 11
Nearly 650 people were awaiting packages of care across Forth
Valley in December 2021.
c. 6,000 hours of care per week was required to meet this need.
A 40% release of current double-handed packages of care in the community equated to 4.5k hours, therefore; addressing 75% of the unresourced care needs at that time.
Problem
Solution

## Slide 12: Timeline
SBAR submission
(end-Oct 21)
Project Team creation
(end-Oct 21)
Pulled relevant representatives together
Governance
(early-Nov 21)
Terms of Reference document agreed and project planning tool created
Engagement Days
(mid-Dec 21)
4x ½ day engagement days attended by c. 200 professionals to provide an overview of model, methodology and opportunity to demo equipment.
Training Delivery
(Jan –mid-Apr 22)
13 x courses delivered by A1Risk Solutions (all while regularly adapting to Covid guidelines)
Compiled and presented to Gold Command. Agreement to progress – budget of £210k.
We achieved this in 5.5 months

## Slide 13: Training
Context
c.200 delegates
20+ teams,
13 training courses
Covid Challenges
Physical Distancing
Attrition rates
Venues
Communications Strategy
Enormous challenge
‘Active Administration’
Relied on teamwork

## Slide 14: Who did we train?
Service area | No. of staff
C&S SW OTs | 11.73%
Falk SW OTs | 8.67%
NHS Comm. AHPs | 28.3%
NHS Acute AHPs | 23%
NHS M&H team | 4%
Provider reps | 10.7%
Falk Care at Home M&H reps | 3%
C&S Reablement M&H reps | 1.5%
FV Learning Disability AHPs | 1%
Falkirk AHPs (new teams) | 8.1%
190 staff

## Slide 15: Training – The Stats
Course | Spaces | Booked | Attended | Passed
1 | 8 | 8 | 6 | 6
2 | 8 | 8 | 8 | 8
3 | 16 | 17 | 17 | 17
4 | 16 | 18 | 16 | 16
5 | 16 | 18 | 16 | 16
6 | 16 | 18 | 18 | 18
7 | 16 | 18 | 15 | 15
8 | 16 | 17 | 17 | 16
9 | 16 | 17 | 16 | 16
10 | 16 | 17 | 16 | 16
11 | 16 | 17 | 14 | 14
12 | 16 | 15 | 15 | 15
13 | 16 | 19 | 16 | 16
Total | 192 | 207 | 190 | 189
Attendance of bookings = 92%
Attendance of capacity = 99%
Pass rate = 99%

## Slide 16: Projected Outcomes
Capacity Release | Upskilled Workforce | Improved Hospital Flow
Through coproduction, undertaking shared training, prescribing dynamic equipment and reviewing current packages of double-handed care; UK evidence indicates that hospital patient flow and provider capacity significantly improves. ​ ​ 644 people are currently awaiting care provision across Forth Valley totalling 5,938 hours. 40% release of current double-handed packages totals 4.4k hours, therefore; addressing 75% of the currently unresourced care needs.​ | Shared knowledge is gained through joint training and streamlining pathways. The subsequent application of these new skills will ensure appropriate assessment of care ​ requirements at point of discharge and in community assessments. This enables ​more impactful change for those using services; easing the demand on ​an already stretched pool of care. | UK evidence indicates that the discharge process speeds up ​ significantly with the embedment of single-handed care. ​ ​ Through enabling capacity release; a projected outcome is reduced ​ admissions to hospital as critical care requirements in the community​ have a greater likelihood of being met.

## Slide 17: Projected Outcomes
Proportionate Assessment Skills | Financial Impact
The ethos behind the Prescribing Proportionate Care model is using the right risk assessment, training and equipment to personalise the prescription of care offered, ensuring the proportionate amount of care is given. ​ ​ Key outcomes to this ergonomic approach are maintenance of the individual’s maximum ​functional independence and the associated health benefits. ​ | All NHS and Partnership staff who completed training successfully were given access to Single Handed Care equipment supplied via JLES minimising unnecessary handovers between teams. ​ ​​ Improving hospital flow and undertaking proportionate assessments ​of care at home requirements enables the Partnerships to maximise ​their care resources and avoid unnecessary costs pertaining to ​unplanned admissions, delayed discharges and emergency respite ​stays.

## Slide 18
Engagement Days
Reviews of Community Double-Handed Packages
Benefits Realisation Analysis Work
1
Co-Production
NHS Forth Valley / Falkirk HSCP / C&SHSCP / Providers
Level 4 ROSPA Accredited 3-Day Training (189 staff)
(Jan 2022 – April 2022)
Pathway Creation
(acute and post-discharge)
Creation of PPC Forums and
access to a Training Suite
(open to AHPs & Providers)
2
3
4
5
6
Co-Production
NHS Forth Valley / Falkirk HSCP / C&SHSCP / Providers

## Slide 19: What should have happened sooner...
Pathway Development |  | 
Two strands required urgent development; the first from discharge to community, the second, for currently provided double-handed community care packages. It was essential that NHS staff were clear on which community team they contact at point of discharge to pick up the review. The most beneficial solution proposed was for the discharging AHP to oversee the discharge until the client is at home to demonstrate use of equipment directly with the care provider and ensure the risk assessment and moving & handling plan are sufficient. This would have been the timeliest solution impacting least on the person in receipt of care, minimising delays and unnecessary transfers between teams. Development of a standardised toolkit for M&H was also advised as NHS Forth Valley, C&SHSCP and Falkirk HSCP use different tools which would support providers across Forth Valley to become familiar more quickly with the paperwork in place.

## Slide 20
Coordination Support |  | 
Dedicated administration coordinator was put forward as essential to fulfil requirements around data collation to inform benefits realisation work and evidence outcomes achieved.​ ​ The functions they would fulfil would be supporting with roll out of developed pathways to staffing groups and acting as the central point of contact around data collation gathering across NHS Forth Valley teams, the HSCPs and Provider groups.
What should have happened sooner...

## Slide 21
Package Reviews |  | 
Undertaking the reviews was cited as a priority for the Partnerships to enable the critical release of care hours.​ ​ A decision was required on how the c. 485 double-handed ​community care packages across Forth Valley were to be undertaken. ​ Pathway development hinged on this and staff attending training ​frequently asked about this.​ ​​ A proposal was written by Practitioner Lead proposing four solutions to complete the double-handed reviews. ​ ​ 1. 5% of trained staff forming review team (12 months) 2.10% forming review team (12 months) 3. Outsourcing reviews to private company 4. Care agencies supporting with reviews
What should have happened sooner...

## Slide 22: Procurement
Despite budget having been approved by Gold Command in Oct 2021; consideration was not given early enough as to how training would be procured.
This issue was raised repeatedly via the Project Team weekly meetings which again highlights the need to have a clear directive from the leadership as to which organisation will procure which services from a very early stage in the development of a project like this.
Procurement legislation provides direction to public bodies and sets out procurement responsibilities / accountabilities. The law is in place to maximise efficiency, save money, be transparent, improve accountability & ensure sustainability.
A business case had to be written with support from the Procurement Team following the decision that Stirling Council would take procurement responsibility for purchasing training. NHS Forth Valley maintained funding responsibility for equipment (as per JLES standard practice).

## Slide 23: Equipment
Training & Community | NHS FV
Robin Gantry with Prism Universal Sling | OHT – MaxiSky with range of slings
Standaid - Minilift 160 - Thorax Seated slings | Standaid – Sara Plus / Sabina
Transfer aid - ReTurn with ReTurn Belt - Etac Raiser and Raiser Belt | Transfer aid – ReTurn
Wendyletts and Sliding sheets | Sliding sheets
Oval Boards | Transfer Boards

## Slide 24: Equipment
Current / Future
Use PT gyms as assessment areas where specific kit not normally available is / can be stored
Review equipment required in Acute and satellite hospitals
Facilitate more robust discharges

## Slide 25: Reflections
Tenacity / Resilience
Clarifying Pathways Earlier
Who We Trained
Environmental Assessments
Remaining Within Scope of Project

## Slide 26: Reflections
Equipment Supply Issues
Language Use
Confidence
Embedding Qualitative Research
Herding Cats (or Tigers)

## Slide 27: “The ones who are crazy enough to think that they can change the world are the ones who do”.
Steve Jobs

## Slide 28: Questions?

## Slide 29: References
ADASS Press Release: Snap Survey reveals a rapidly deteriorating picture of Social Care Services. 29th November 2021. Accessed 13th December 2021 at Adass
Box, M., Agnew, L. (2019) Worth a second look? Occupational Therapy News 27 (11):16-18. The Care Act (2014) Available at: https://www.gov.uk/government/publications/care-act2014-part-1-factsheets Accessed 11 September 2020.
CQC State of Care | Care Quality Commission (cqc.org.uk) Accessed January 5th 2022
Daley, J. (2019) Single-handed care. Conference proceedings 27th November 2019. Accessed 11th October 2020. at https://www.theotshow.com/2019-education-programme
Hague C, Charlton C, Billing R, Bone L, Cambridge S Conference Presentation (2015) RCOT
Harrison, D. (2017) Single-handed care: it is a vision or a reality. Parts 1. Column, Volume 29, Issue 4, 2017
Harrison, D. (2018) Single-handed care: it is a vision or a reality. Parts 2. Column, Volume 30, Issue 1, 2018
Harrison, D. (2020) Single-handed care winning formula Part one. January 22nd Accessed October 23rd at http://attoday.co.uk/single-handed-care-part-one-the-winning-formula/ Harrison,
Harrison, D, Webb, J. (2020) Single-handed care the winning formula.
Part two. May 20th Accessed October 16th at http://attoday.co.uk/single-handed-care-part-two-the-winningformula/
Harrison, D (2020) Single-Handed Care what works: A discussion paper. 17th December 2020 Accessed 23rd January 2021 https://www.inclusion.me.uk/news/single_handed_care_what_works
Health and Safety Executive (2004) Manual handling: manual handling operations regulations 1992 (as amended). Guidance on regulations. (L23) 3rd ed. London: H.S.E. Handling Operations Regulations,1992.

## Slide 30: References (pg.2)
Mandelstam, (M) (2018) Single-handed care. Solution, salvation, poisoned chalice-or simply nothing to write home about? Column 30(4):6-10. inclusion.me, November 2020 30
Mandelstam, M (2020) Manual Handling, Single-Handed Care, Occupational Therapy And The Law: 2020 And Beyond: A Discussion Paper. 1st October 2020 Accessed 1st October 2020 https://www.inclusion.me.uk/news/manual_handling_single_handed_care_occupational_t herapy_and_the_law
Nuffield Trust (2021) Invisible crisis in home care unfolding as social care sector loses up to 50,000 staff in lead up to winter months 1st December 2021 Accessed 5th January 2022 at Invisible crisis in home care unfolding as social care sector loses up to 50,000 staff in lead up to winter months | The Nuffield Trust
Outhwaite, C., Harrison, D. (2018) The development of a community assessment tool. Conference proceeding. March 18th 2018. Accessed 15th September 16th 2020 at https://issuu.com/prysmgroupltd/docs/naidex_pro_highlight-showguide_
Sefton Council (2019) Sefton Council holding free workshop on new care approach. 22nd January 2019 Accessed September 15th 2020. athttps://mysefton.co.uk/2019/01/22/seftoncouncil-holding-free-workshop-on-new-care-approach/
Webb, J., Harrison, D., Szczepura,K.(2016) An online Manual handling Toolkit to Improve skills and reduce risks, EHF, London, Uk. Conference details available from: https://ehf2016.exordo.com/files/papers/26/final_draft/026.pdf Ergonomics and Human Factors Conference 2016.
Webb, J., Harrison, D. (2019) The Salford Moving and handling Competency Passport ISBN 978-1-912337-26-2
Webb et al (2022) Improving Competency in Safe Patient Handling Through Online Learning Beyond the Classroom: A Longitudinal Study.( o Webb, Peter Hogg, Martin Twiste, Elon Correa. The American Journal of Occupational Therapy, 2022, Vol. 76(2), 7602205160. https://doi.org/10.5014/ajot.2022.044388